## TASK LIST
DILSTON SOFTWARE ENGINEERING PRACTICE
Task | Deadline | Priority | Person | Dependency | Status | Timeline
Skills Audit & Proposal Milestone | 2023-02-17 | HIGH | ALL |  | DONE | 01/02/2023 - 17/02/2023
View the skills audit template | 2023-02-06 | HIGH | ALL |  | DONE | 01/02/2023 - 06/02/2023
Ensure all team members fill out their section of the skills audit | 2023-02-12 | HIGH | ALL | View the skills audit template | DONE | 06/02/2023 - 12/02/2023
Chat with team about the project idea & proposal | 2023-02-13 | MEDIUM | ALL |  | DONE | 12/02/2023 - 13/02/2023
Upon team agreement upon project idea, fill out the proposal section | 2023-02-14 | HIGH | ALL | Chat with team about the project idea & proposal | DONE | 13/02/2023 - 14/02/2023
Ensure the skills audit is completed | 2023-02-15 | HIGH | ALL | Ensure all team members fill out their section of the skills audit Upon team agreement upon project idea, fill out the proposal section | DONE | 14/02/2023 - 15/02/2023
Hand in the skills audit | 2023-02-16 | HIGH | ALL | Ensure the skills audit is completed | DONE | 15/02/2023 - 16/02/2023
Skills audit contingency (1 days) | 2023-02-17 | LOW | ALL |  | DONE | 16/02/2023 - 17/02/2023
Organising Team Meetings/Communication Milestone | 2023-02-16 | HIGH | ALL |  | DONE
Find out availability from each member | 2023-02-15 | HIGH | PAWEL LASOTA |  | DONE
Plan regular weekly meetings that match availability | 2023-02-16 | MEDIUM | PAWEL LASOTA | Find out availability from each member | DONE
Code of Conduct Milestone | 2023-02-20 | HIGH | PAWEL LASOTA |  | DONE
View code of conduct examples |  | LOW | PAWEL LASOTA |  | DONE
Create a CoC document stating guidelines & rules within the team |  | HIGH | PAWEL LASOTA |  | DONE
Ensure the document is signed by all team members |  | HIGH | PAWEL LASOTA | Create a CoC document stating guidelines & rules within the team | DONE
Code of Conduct Documentation Contingency (1 day) |  | LOW | PAWEL LASOTA |  | DONE
Risk Analysis Milestone | 2023-02-25 | HIGH | PAWEL LASOTA |  | IN PROGRESS
Research examples of risk analysis documentation |  | LOW | PAWEL LASOTA |  | IN PROGRESS
Create a new word document |  | LOW | PAWEL LASOTA |  | IN PROGRESS
List possible risks |  | HIGH | PAWEL LASOTA |  | IN PROGRESS
Describe possible risks |  | HIGH | PAWEL LASOTA | List possible risks | IN PROGRESS
Work out probability of risks |  | MEDIUM | PAWEL LASOTA | List possible risks | IN PROGRESS
Work out severity of risks |  | MEDIUM | PAWEL LASOTA | List possible risks | IN PROGRESS
Include possible solutions/resolve to these risks |  | HIGH | PAWEL LASOTA | List possible risks | IN PROGRESS
Project Ideation Milestone |  |  | PAWEL LASOTA |  | TO BE DONE
Research possible solutions
Solution Design Milestone |  |  | JOSH MARFLEET |  | TO BE DONE
Baseline Implementation Milestone |  |  | JACK WELCH |  | IN PROGRESS
Create a new python project using pyCharm named Face_Recognition |  |  | JACK WELCH |  | IN PROGRESS
Create an environment via anaconda for this project |  |  | JACK WELCH | Create a new python project using pyCharm named Face_Recognition | IN PROGRESS
Download all necessary libraries |  |  | JACK WELCH | Create an environment via anaconda for this project | IN PROGRESS
Connect the pyCharm project to github for easy collaboration |  |  | JACK WELCH |  | IN PROGRESS
Test the project can be collaborated with via github |  |  | JACK WELCH | Connect the pyCharm project to github for easy collaboration | IN PROGRESS
Iterative Development (Team) Milestone |  |  | ALL |  | TO BE DONE
Solution Testing Milestone |  |  | JACK WELCH |  | TO BE DONE
User Interface Milestone |  |  | CHARLIE JACK |  | TO BE DONE
Ethical Evaluation Milestone |  |  | JOSH MARFLEET |  | TO BE DONE
Solution Review Milestone |  |  | CHARLIE JACK |  | TO BE DONE
Hand-In Milestone | 2023-05-08 |  | ALL |  | STUCK
Ensure document is completed
Hand in document

## GANTT CHART
DILSTON SOFTWARE ENGINEERING PRACTICE GANTT CHART
[7 empty] | WEEK 1 | [6 empty] | WEEK 2
[5 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18
[5 empty] | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T
Task | Lead | Timeline | Status | Days
Skills Audit & Proposal Milestone | ALL | 01/02/2023 - 17/02/2023 | DONE | 17
View the skills audit template | ALL | 01/02/2023 - 06/02/2023 | DONE | 6 | bar: 1 M to WEEK 1 6 S
Ensure all team members fill out their section of the skills audit | ALL | 06/02/2023 - 12/02/2023 | DONE | 6 | bar: WEEK 1 6 S to WEEK 2 12 F
Chat with team about the project idea & proposal | ALL | 12/02/2023 - 13/02/2023 | DONE | 1 | bar: WEEK 2 13 S to WEEK 2 14 S
Upon team agreement upon project idea, fill out the proposal section | ALL | 13/02/2023 - 14/02/2023 | DONE | 1 | bar: WEEK 2 14 S to WEEK 2 15 M
Ensure the skills audit is completed | ALL | 14/02/2023 - 15/02/2023 | DONE | 1 | bar: WEEK 2 15 M to WEEK 2 16 T
Hand in the skills audit | ALL | 15/02/2023 - 16/02/2023 | DONE | 1 | bar: WEEK 2 16 T to WEEK 2 17 W
Skills audit contingency (2 days) | ALL | 16/02/2023 - 17/02/2023 | DONE | 1
Hand-In Milestone

## KEY
Status | STATUS | MEMBERS
DONE | HIGH | PAWEL LASOTA
IN PROGRESS | MEDIUM | JACK WELCH
TO BE DONE | LOW | CHARLIE JACK
STUCK |  | JOSH MARFLEET
ALL