## TASK LIST
DILSTON SOFTWARE ENGINEERING PRACTICE
Task | Deadline | Priority | Person | Dependency | Status | Timeline
Skills Audit & Proposal Milestone | 2023-02-17 | HIGH | ALL |  | DONE | 01/02/2023 - 17/02/2023
View the skills audit template | 2023-02-06 | HIGH | ALL |  | DONE | 01/02/2023 - 06/02/2023
Ensure all team members fill out their section of the skills audit | 2023-02-10 | HIGH | ALL | View the skills audit template | DONE | 06/02/2023 - 10/02/2023
Fill out the team strengths & weaknesses at bottom of skills audit | 2023-02-12 | HIGH | PAWEL LASOTA | Ensure all team members fill out their section of the skills audit | DONE | 10/02/2023 - 12/02/2023
Fill out project manager comments on the team at bottom of skills audit | 2023-02-12 | HIGH | PAWEL LASOTA | Ensure all team members fill out their section of the skills audit | DONE | 10/02/2023 - 12/02/2023
Chat with team about the project idea & proposal | 2023-02-13 | HIGH | ALL |  | DONE | 12/02/2023 - 13/02/2023
Upon team agreement upon project idea, fill out the proposal section | 2023-02-14 | HIGH | PAWEL LASOTA | Chat with team about the project idea & proposal | DONE | 13/02/2023 - 14/02/2023
Ensure the skills audit is completed | 2023-02-15 | HIGH | PAWEL LASOTA | Ensure all team members fill out their section of the skills audit & Upon team agreement upon project idea, fill out the proposal section | DONE | 14/02/2023 - 15/02/2023
Hand in the skills audit | 2023-02-16 | HIGH | PAWEL LASOTA | Ensure the skills audit is completed | DONE | 15/02/2023 - 16/02/2023
Skills audit contingency (1 days) | 2023-02-17 | LOW | ALL |  | DONE | 16/02/2023 - 17/02/2023
Organising Team Meetings/Communication Milestone | 2023-02-16 | HIGH | ALL |  | DONE | 07/02/2023 - 16/02/2023
Find out availability from each member | 2023-02-07 | HIGH | PAWEL LASOTA |  | DONE | 07/02/2023 - 08/02/2023
Plan regular weekly meetings that match availability | 2023-02-11 | MEDIUM | PAWEL LASOTA | Find out availability from each member | DONE | 08/02/2023 - 11/02/2023
Ask all team members whether they are happy communicating with Discord | 2023-02-14 | MEDIUM | PAWEL LASOTA |  | DONE | 11/02/2023 - 14/02/2023
Contingency Time (2 days) | 2023-02-16 | LOW | PAWEL LASOTA |  | DONE | 14/02/2023 - 16/02/2023
Project Ideation Milestone | 2023-03-27 | HIGH | PAWEL LASOTA |  | DONE | 10/02/2023 - 27/03/2023
Start writing up a problem statement | 2023-02-10 | MEDIUM | PAWEL LASOTA |  | DONE | 10/02/2023 - 10/02/2023
In the project statement, state the idea and issue at hand | 2023-02-10 | MEDIUM | PAWEL LASOTA |  | DONE | 10/02/2023 - 10/02/2023
Start writing up the problem motivation | 2023-02-11 | LOW | PAWEL LASOTA |  | DONE | 10/02/2023 - 11/02/2023
In the problem motivation, state why we're doing what we're doing | 2023-02-11 | LOW | PAWEL LASOTA |  | DONE | 11/02/2023 - 11/02/2023
Start thinking about the Literature Review for different solutions | 2023-02-12 | MEDIUM | PAWEL LASOTA |  | DONE | 11/02/2023 - 12/02/2023
Research existing solutions to face recognition | 2023-02-13 | HIGH | PAWEL LASOTA |  | DONE | 12/02/2023 - 13/02/2023
Identify the face recognition techniques these solutions have used | 2023-02-14 | HIGH | PAWEL LASOTA | Research existing solutions to face recognition | DONE | 13/02/2023 - 14/02/2023
Find multiple techniques | 2023-02-14 | HIGH | PAWEL LASOTA |  | DONE | 13/02/2023 - 14/02/2023
Explain using references what the techniques consists of | 2023-03-15 | HIGH | PAWEL LASOTA | Identify the face recognition techniques these solutions have used | DONE | 14/02/2023 - 15/03/2023
Identify the strengths of each technique | 2023-03-15 | HIGH | PAWEL LASOTA | Identify the face recognition techniques these solutions have used | DONE | 14/02/2023 - 15/03/2023
Identify the weaknessess of each technique | 2023-03-15 | HIGH | PAWEL LASOTA | Identify the face recognition techniques these solutions have used | DONE | 14/02/2023 - 15/03/2023
Write up the technique, strengths and weaknesses | 2023-03-15 | HIGH | PAWEL LASOTA | Identify the face recognition techniques these solutions have used | DONE | 14/02/2023 - 15/03/2023
Compare the techniques and identify which one is better in which scenario | 2023-03-15 | HIGH | PAWEL LASOTA | Write up the technique, strengths and weaknesses | DONE | 14/02/2023 - 15/03/2023
Write up a conclusion as a takeaway for the reader | 2023-03-15 | MEDIUM | PAWEL LASOTA | Write up the technique, strengths and weaknesses | DONE | 14/02/2023 - 15/03/2023
Write up a project statement | 2023-03-20 | MEDIUM | PAWEL LASOTA |  | DONE | 15/03/2023 - 20/03/2023
Contingency Time (7 days) | 2023-03-27 | LOW | PAWEL LASOTA |  | DONE | 20/03/2023 - 27/03/2023
Solution Design Milestone | 2023-03-22 | HIGH | JOSH MARFLEET |  | DONE | 10/02/2023 - 22/03/2023
View the Solution Design Specification brief | 2023-02-10 | HIGH | JOSH MARFLEET |  | DONE | 10/02/2023 - 10/02/2023
Research examples of solution designing online | 2023-02-10 | MEDIUM | JOSH MARFLEET | View the Solution Design Specification brief | DONE | 10/02/2023 - 10/02/2023
Create a draw.io page | 2023-02-11 | MEDIUM | JOSH MARFLEET |  | DONE | 10/02/2023 - 11/02/2023
Plot a flowchart of what the project will look like step by step | 2023-02-11 | HIGH | JOSH MARFLEET | Create a draw.io page | DONE | 11/02/2023 - 11/02/2023
Implement the flowchart into a word document | 2023-02-20 | LOW | JOSH MARFLEET | Plot a flowchart of what the project will look like step by step | DONE | 11/02/2023 - 20/02/2023
Create a solution description | 2023-02-21 | MEDIUM | JOSH MARFLEET | View the Solution Design Specification brief | DONE | 20/02/2023 - 21/02/2023
Describe the functionality of the solution | 2023-02-22 | MEDIUM | JOSH MARFLEET | Create a solution description | DONE | 21/02/2023 - 22/02/2023
Create a data description of what kind of data will be used | 2023-02-28 | HIGH | JOSH MARFLEET | View the Solution Design Specification brief | DONE | 22/02/2023 - 28/02/2023
Explain why we will use this data | 2023-03-05 | HIGH | JOSH MARFLEET | Create a data description of what kind of data will be used | DONE | 28/02/2023 - 05/03/2023
Discuss the solution motivation | 2023-03-10 | MEDIUM | JOSH MARFLEET | View the Solution Design Specification brief | DONE | 05/03/2023 - 10/03/2023
Explain why we decided to do this project | 2023-03-15 | MEDIUM | JOSH MARFLEET | Discuss the solution motivation | DONE | 10/03/2023 - 15/03/2023
Contingency Time (7 days) | 2023-03-22 | LOW | JOSH MARFLEET |  | DONE | 15/03/2023 - 22/03/2023
Baseline Implementation Milestone | 2023-03-27 | HIGH | JACK WELCH |  | DONE | 10/02/2023 - 20/03/2023
Create a new python project using pyCharm named Face_Recognition | 2023-02-10 | LOW | JACK WELCH |  | DONE | 10/02/2023 - 10/02/2023
Create an environment via anaconda for this project | 2023-02-10 | LOW | JACK WELCH | Create a new python project using pyCharm named Face_Recognition | DONE | 10/02/2023 - 10/02/2023
Find a pre-built face recognition library | 2023-02-13 | MEDIUM | JACK WELCH |  | DONE | 10/02/2023 - 13/02/2023
Download all necessary libraries | 2023-02-13 | HIGH | JACK WELCH | Create an environment via anaconda for this project | DONE | 13/02/2023 - 13/02/2023
Connect the pyCharm project to github for easy collaboration | 2023-02-14 | MEDIUM | JACK WELCH |  | DONE | 13/02/2023 - 14/02/2023
Test the project can be collaborated/viewed with via github | 2023-02-14 | MEDIUM | JACK WELCH | Connect the pyCharm project to github for easy collaboration | DONE | 14/02/2023 - 14/02/2023
Import the necessary libraries | 2023-02-15 | HIGH | JACK WELCH | Download all necessary libraries | DONE | 14/02/2023 - 15/02/2023
Find a dataset for baseline | 2023-02-20 | HIGH | JACK WELCH |  | DONE | 15/02/2023 - 20/02/2023
Ensure the dataset is in the correct format - subfolders with class names | 2023-02-20 | HIGH | JACK WELCH | Find a dataset for baseline | DONE | 20/02/2023 - 20/02/2023
Ensure each class/person has enough images to train on | 2023-02-20 | HIGH | JACK WELCH |  | DONE | 20/02/2023 - 20/02/2023
Program a face detection/extraction algorithm | 2023-03-02 | HIGH | JACK WELCH |  | DONE | 20/02/2023 - 02/03/2023
Program the recognition aspect using the dataset | 2023-03-10 | HIGH | JACK WELCH | Ensure the dataset is in the correct format - subfolders with class names | DONE | 02/03/2023 - 10/03/2023
Program the webcam so that the app opens it | 2023-03-12 | HIGH | JACK WELCH |  | DONE | 10/03/2023 - 12/03/2023
Program the face detection into the webcam | 2023-03-15 | HIGH | JACK WELCH |  | DONE | 12/03/2023 - 15/03/2023
Program the face recognition into the webcam | 2023-03-15 | HIGH | JACK WELCH | Program the face detection into the webcam | DONE | 15/03/2023 - 15/03/2023
Evaluate the solution | 2023-03-20 | HIGH | JACK WELCH | Program the face recognition into the webcam | DONE | 16/03/2023 - 20/03/2023
Contingency Time (7 days) | 2023-03-27 | LOW | JACK WELCH |  | DONE | 20/03/2023 - 27/03/2023
Iterative Development (Team) Milestone | 2023-04-25 | HIGH | ALL |  | TO BE DONE | 23/03/2023 - 25/04/2023
All members to read & understand the iterative development specification | 2023-03-24 | HIGH | ALL |  | TO BE DONE | 23/03/2023 - 24/03/2023
Look online for face recognition examples | 2023-03-24 | LOW | ALL |  | TO BE DONE | 23/03/2023 - 24/03/2023
Find a small faces dataset that will be used for training the solution | 2023-03-24 | HIGH | ALL |  | TO BE DONE | 23/03/2023 - 24/03/2023
Using the same environment as in baseline, import necessary libraries | 2023-03-24 | HIGH | ALL |  | TO BE DONE | 23/03/2023 - 24/03/2023
Implement code to access the dataset | 2023-03-25 | HIGH | ALL | Find a small faces dataset that will be used for training the solution | TO BE DONE | 24/03/2023 - 25/03/2023
Normalise the dataset | 2023-03-25 | HIGH | ALL | Implement code to access the dataset | TO BE DONE | 24/03/2023 - 25/03/2023
Resize the dataset so all images are the same size | 2023-03-25 | HIGH | ALL | Implement code to access the dataset | TO BE DONE | 24/03/2023 - 25/03/2023
Augment the data by e.g. tilting the images | 2023-03-25 | HIGH | ALL | Implement code to access the dataset | TO BE DONE | 24/03/2023 - 25/03/2023
Implement code to split the training and testing data with a ratio of 80:20 | 2023-03-25 | HIGH | ALL | Normalise the dataset | TO BE DONE | 24/03/2023 - 25/03/2023
Extract/detect the faces in all images | 2023-03-26 | HIGH | ALL |  | TO BE DONE | 25/03/2023 - 26/03/2023
Implement a CNN sequential model (Mini-Milestone) | 2023-03-28 | HIGH | ALL |  | TO BE DONE | 26/03/2023 - 28/03/2023
Create multiple convolutional (Conv2D) layers | 2023-03-27 | HIGH | ALL | Implement a CNN sequential model | TO BE DONE | 26/03/2023 - 27/03/2023
Specify the number of filters, kernel_size, activation methods, input shapes | 2023-03-27 | HIGH | ALL |  | TO BE DONE | 26/03/2023 - 27/03/2023
Create multiple MaxPooling2D layers | 2023-03-27 | HIGH | ALL |  | TO BE DONE | 26/03/2023 - 27/03/2023
Specify the pool size of each max pooling layer | 2023-03-27 | HIGH | ALL |  | TO BE DONE | 26/03/2023 - 27/03/2023
Implement a Flatten function | 2023-03-28 | HIGH | ALL |  | TO BE DONE | 27/03/2023 - 28/03/2023
Create multiple Dense layers with a relu activation | 2023-03-28 | HIGH | ALL |  | TO BE DONE | 27/03/2023 - 28/03/2023
Implemet multiple dropouts of around 0.5 to prevent overfitting | 2023-03-28 | HIGH | ALL |  | TO BE DONE | 27/03/2023 - 28/03/2023
Compile the CNN model | 2023-03-28 | HIGH | ALL |  | TO BE DONE | 27/03/2023 - 28/03/2023
Train the CNN model using model.fit function | 2023-03-29 | HIGH | ALL | Implement a CNN sequential model (Mini-Milestone) | TO BE DONE | 28/03/2023 - 29/03/2023
Specify the batch size, epochs, steps_per_epoch, training and validation data | 2023-03-29 | HIGH | ALL |  | TO BE DONE | 28/03/2023 - 29/03/2023
Evaluate the model via a graph with accuracy as y label and epoch as x label | 2023-03-30 | HIGH | ALL | Train the CNN model using model.fit function | TO BE DONE | 29/03/2023 - 30/03/2023
Evaluate the model via a graph with model loss as y being loss and x being epoch | 2023-03-30 | HIGH | ALL | Train the CNN model using model.fit function | TO BE DONE | 29/03/2023 - 30/03/2023
Using the model use the .predict() function to predict test data based on training data | 2023-03-30 | HIGH | ALL | Train the CNN model using model.fit function | TO BE DONE | 29/03/2023 - 30/03/2023
Create a confusion matrix | 2023-03-31 | HIGH | ALL | Using the model use the .predict() function to predict test data based on training data | TO BE DONE | 30/03/2023 - 31/03/2023
Calculate the accuracy based on the confusion matrix | 2023-03-31 | HIGH | ALL | Create a confusion matrix | TO BE DONE | 30/03/2023 - 31/03/2023
Implement code to access the webcam (Mini-Milestone) | 2023-04-01 | HIGH | ALL |  | TO BE DONE | 31/03/2023 - 01/04/2023
Implement code for validation whether webcam is available | 2023-03-31 | HIGH | ALL |  | TO BE DONE | 31/03/2023 - 31/03/2023
Implement code to capture each frame of the webcam | 2023-03-31 | HIGH | ALL |  | TO BE DONE | 31/03/2023 - 31/03/2023
Convert each frame to grayscale | 2023-03-31 | HIGH | ALL | Implement code to capture each frame of the webcam | TO BE DONE | 31/03/2023 - 31/03/2023
Detect faces within the frame based on the feature extraction methodology | 2023-04-01 | HIGH | ALL | Convert each frame to grayscale | TO BE DONE | 01/04/2023 - 01/04/2023
Implement a for loop for each frame to convert to gray and resize face to required dimensions | 2023-04-01 | HIGH | ALL |  | TO BE DONE | 01/04/2023 - 01/04/2023
Predict the face using the model | 2023-04-01 | HIGH | ALL |  | TO BE DONE | 01/04/2023 - 01/04/2023
Calculate the confidence and display it | 2023-04-01 | HIGH | ALL | Predict the face using the model | TO BE DONE | 01/04/2023 - 01/04/2023
Create a confidence threshold with over 90 being confident enough to predict | 2023-04-01 | HIGH | ALL | Create a confidence threshold with over 90 being confident enough to predict | TO BE DONE | 01/04/2023 - 01/04/2023
Else, the confidence under 90 will be considered 'unknown' | 2023-04-01 | HIGH | ALL |  | TO BE DONE | 01/04/2023 - 01/04/2023
Display the frame | 2023-04-01 | HIGH | ALL |  | TO BE DONE | 01/04/2023 - 01/04/2023
Use other novel pre-processing techniques and test the accuracy again | 2023-04-04 | HIGH | ALL |  | TO BE DONE | 01/04/2023 - 04/04/2023
Change the CNN model to pre-built CNN models such as resnet for comparison | 2023-04-10 | HIGH | ALL | Implement a CNN sequential model | TO BE DONE | 04/04/2023 - 10/04/2023
Change the code accordingly to make the pre-built model work | 2023-04-10 | HIGH | ALL | Change the CNN model to pre-built CNN models such as resnet for comparison | TO BE DONE | 04/04/2023 - 10/04/2023
Test the accuracy with at least one other model | 2023-04-10 | HIGH | ALL | Change the CNN model to pre-built CNN models such as resnet for comparison | TO BE DONE | 04/04/2023 - 10/04/2023
Write down the impact of changing pre-processing of data methodologies on the accuracy | 2023-04-11 | HIGH | ALL | Use other novel pre-processing techniques and test the accuracy again | TO BE DONE | 10/04/2023 - 11/04/2023
Compare & Evaluate different pre-processing techniques in a document | 2023-04-13 | HIGH | ALL | Write down the impact of changing pre-processing of data methodologies on the accuracy | TO BE DONE | 11/04/2023 - 13/04/2023
Write down the impact of changing the CNN model to pre-built CNN models | 2023-04-13 | HIGH | ALL | Test the accuracy with at least one other model | TO BE DONE | 11/04/2023 - 13/04/2023
Compare & Evaluate the different models and comparisons | 2023-04-15 | HIGH | ALL | Write down the impact of changing the CNN model to pre-built CNN models | TO BE DONE | 13/04/2023 - 15/04/2023
Tune parameters for each model to see which parameters are best | 2023-04-17 | HIGH | ALL | Change the CNN model to pre-built CNN models such as resnet for comparison | TO BE DONE | 15/04/2023 - 17/04/2023
Document and justify the changes for parameters, e.g. better accuracy | 2023-04-17 | HIGH | ALL |  | TO BE DONE | 15/04/2023 - 17/04/2023
Implement an appendix in the word document with code | 2023-04-18 | MEDIUM | ALL |  | TO BE DONE | 17/04/2023 - 18/04/2023
Ensure the work is well documented and results well organised | 2023-04-18 | MEDIUM | ALL |  | TO BE DONE | 17/04/2023 - 18/04/2023
Contingency Time (7 days) | 2023-04-25 | LOW | ALL |  | TO BE DONE | 18/04/2023 - 25/04/2023
Solution Testing Milestone | 2023-05-05 | HIGH | JACK WELCH |  | TO BE DONE | 18/04/2023 - 05/05/2023
Read the Solution Testing specification from the assignment brief | 2023-04-18 | HIGH | JACK WELCH |  | TO BE DONE | 18/04/2023 - 18/04/2023
Create a word document with a table for a test plan | 2023-04-19 | HIGH | JACK WELCH |  | TO BE DONE | 18/04/2023 - 19/04/2023
The headings of the table should involve what you are going to test and results | 2023-04-19 | HIGH | JACK WELCH | Create a word document with a table for a test plan | TO BE DONE | 18/04/2023 - 19/04/2023
Create test cases for identifying flaws | 2023-04-19 | HIGH | JACK WELCH |  | TO BE DONE | 18/04/2023 - 19/04/2023
Write the test cases into the table | 2023-04-19 | HIGH | JACK WELCH | Create test cases for identifying flaws | TO BE DONE | 18/04/2023 - 19/04/2023
Perform required tests on all of these test cases | 2023-04-23 | HIGH | JACK WELCH | Create test cases for identifying flaws | TO BE DONE | 19/04/2023 - 23/04/2023
Write down what you have found regarding these tests | 2023-04-23 | MEDIUM | JACK WELCH | Perform required tests on all of these test cases | TO BE DONE | 19/04/2023 - 23/04/2023
Create a report discussing your findings | 2023-04-23 | HIGH | JACK WELCH | Write down what you have found regarding these tests | TO BE DONE | 19/04/2023 - 23/04/2023
Discuss your recommendations based on the results | 2023-04-23 | HIGH | JACK WELCH | Create a report discussing your findings | TO BE DONE | 19/04/2023 - 23/04/2023
Ensure your justification is worthwile and suitable for purpose | 2023-04-23 | MEDIUM | JACK WELCH | Discuss your recommendations based on the results | TO BE DONE | 19/04/2023 - 23/04/2023
Ensure your recommendations will help improve the system | 2023-04-23 | HIGH | JACK WELCH | Ensure your justification is worthwile and suitable for purpose | TO BE DONE | 19/04/2023 - 23/04/2023
Ensure the document is clear and results are well analysed | 2023-04-23 | MEDIUM | JACK WELCH |  | TO BE DONE | 19/04/2023 - 23/04/2023
Perform further tests that will have a purpose of confusing the model | 2023-04-27 | MEDIUM | JACK WELCH |  | TO BE DONE | 23/04/2023 - 27/04/2023
Discuss your findings in the document about these further tests | 2023-04-27 | MEDIUM | JACK WELCH | Perform further tests that will have a purpose of confusing the model | TO BE DONE | 23/04/2023 - 27/04/2023
Discuss your recommendations on improving the model itself | 2023-04-27 | MEDIUM | JACK WELCH | Discuss your findings in the document about these further tests | TO BE DONE | 23/04/2023 - 27/04/2023
Finalise your discussion with a conclusion summarising the tests | 2023-04-28 | MEDIUM | JACK WELCH |  | TO BE DONE | 27/04/2023 - 28/04/2023
Contingency Time (7 days) | 2023-05-05 | LOW | JACK WELCH |  | TO BE DONE | 28/04/2023 - 05/05/2023
User Interface Milestone | 2023-03-27 | HIGH | CHARLIE JACK |  | DONE | 10/02/2023 - 27/03/2023
Read the UI specification from the assignment brief | 2023-02-10 | HIGH | CHARLIE JACK |  | DONE | 10/02/2023 - 10/02/2023
Research relevant examples of UI for face recognition | 2023-02-11 | MEDIUM | CHARLIE JACK | Read the UI specification from the assignment brief | DONE | 10/02/2023 - 11/02/2023
Find a good UI software for integration | 2023-02-11 | HIGH | CHARLIE JACK |  | DONE | 11/02/2023 - 11/02/2023
Find a tutorial on how to use the software and learn it a little | 2023-02-20 | MEDIUM | CHARLIE JACK | Find a good UI software for integration | DONE | 11/02/2023 - 20/02/2023
Communicate with others on the vision of the application to provide good UI | 2023-02-21 | MEDIUM | CHARLIE JACK |  | DONE | 20/02/2023 - 21/02/2023
Design the UI using low fidelity prototyping | 2023-02-23 | MEDIUM | CHARLIE JACK |  | DONE | 21/02/2023 - 23/02/2023
Design the UI using high fidelity prototyping | 2023-02-26 | MEDIUM | CHARLIE JACK | Design the UI using low fidelity prototyping | DONE | 23/02/2023 - 26/02/2023
Create justifications for why the design is being designed this way | 2023-02-27 | HIGH | CHARLIE JACK | Design the UI using high fidelity prototyping | DONE | 26/02/2023 - 27/02/2023
Communicate with others about the designs | 2023-02-28 | MEDIUM | CHARLIE JACK |  | DONE | 27/02/2023 - 28/02/2023
Ensure the designs show signs of ease of use | 2023-03-02 | MEDIUM | CHARLIE JACK | Design the UI using high fidelity prototyping | DONE | 28/02/2023 - 02/03/2023
Integrate the design into a programming software | 2023-03-10 | HIGH | CHARLIE JACK |  | DONE | 02/03/2023 - 10/03/2023
Program relevant buttons and other interactions | 2023-03-15 | HIGH | CHARLIE JACK | Integrate the design into a programming software | DONE | 10/03/2023 - 15/03/2023
Test the interaction yourself and with the team to ensure good interactivity | 2023-03-17 | HIGH | CHARLIE JACK | Program relevant buttons and other interactions | DONE | 15/03/2023 - 17/03/2023
Log the tests to show progress of improvements | 2023-03-18 | HIGH | CHARLIE JACK | Test the interaction yourself and with the team to ensure good interactivity | DONE | 17/03/2023 - 18/03/2023
Discuss the testing and justify any changes made | 2023-03-20 | HIGH | CHARLIE JACK | Log the tests to show progress of improvements | DONE | 18/03/2023 - 20/03/2023
Contingency Time (7 days) | 2023-03-27 | LOW | CHARLIE JACK |  | DONE | 20/03/2023 - 27/03/2023
Ethical Evaluation Milestone | 2023-05-05 | HIGH | JOSH MARFLEET |  | TO BE DONE | 18/04/2023 - 05/05/2023
Read the Ethical Evaluation Specification from the assignment brief | 2023-04-18 | HIGH | JOSH MARFLEET |  | TO BE DONE | 18/04/2023 - 18/04/2023
Read into bias analysis on the internet | 2023-04-19 | LOW | JOSH MARFLEET |  | TO BE DONE | 18/04/2023 - 19/04/2023
Discuss input data used in the model | 2023-04-19 | HIGH | JOSH MARFLEET |  | TO BE DONE | 18/04/2023 - 19/04/2023
Discuss how this input data is augmentated and how it prevents bias | 2023-04-19 | HIGH | JOSH MARFLEET | Discuss input data used in the model | TO BE DONE | 19/04/2023 - 20/04/2023
Discuss how the data is normalised to prevent bias | 2023-04-20 | HIGH | JOSH MARFLEET | Discuss input data used in the model | TO BE DONE | 19/04/2023 - 20/04/2023
Discuss any other techniques that are used that could potentially prevent bias | 2023-04-20 | HIGH | JOSH MARFLEET |  | TO BE DONE | 19/04/2023 - 20/04/2023
Discuss any improvements into the solution that could further prevent bias | 2023-04-20 | HIGH | JOSH MARFLEET |  | TO BE DONE | 20/04/2023 - 21/04/2023
Discuss why preventing bias is important | 2023-04-21 | MEDIUM | JOSH MARFLEET | Read into bias analysis on the internet | TO BE DONE | 20/04/2023 - 21/04/2023
Read into common ethical issues in face recognition | 2023-04-21 | LOW | JOSH MARFLEET |  | TO BE DONE | 20/04/2023 - 21/04/2023
Write about multiple of these ethical issues you have researched | 2023-04-21 | LOW | JOSH MARFLEET | Read into common ethical issues in face recognition | TO BE DONE | 20/04/2023 - 21/04/2023
Write why ethics is important to discuss | 2023-04-21 | HIGH | JOSH MARFLEET | Read into common ethical issues in face recognition | TO BE DONE | 21/04/2023 - 22/04/2023
Give examples of ethical problems other solutions have experienced in face recognition and the consequences | 2023-04-22 | LOW | JOSH MARFLEET |  | TO BE DONE | 21/04/2023 - 22/04/2023
Look into the solution and identify ethical problems | 2023-04-22 | HIGH | JOSH MARFLEET | Give examples of ethical problems other solutions have experienced in face recognition and the consequences | TO BE DONE | 21/04/2023 - 22/04/2023
If possible, fix these identified problems - If willing, incorporate state-of-the-art third party tools to correct model bias | 2023-04-25 | HIGH | JOSH MARFLEET | Look into the solution and identify ethical problems | TO BE DONE | 22/04/2023 - 25/04/2023
Discuss the identified problems and the fixes | 2023-04-25 | HIGH | JOSH MARFLEET | If possible, fix these identified problems - If willing, incorporate state-of-the-art third party tools to correct model bias | TO BE DONE | 22/04/2023 - 25/04/2023
Compare the results prior the fixes and after | 2023-04-26 | MEDIUM | JOSH MARFLEET | Discuss the identified problems and the fixes | TO BE DONE | 25/04/2023 - 26/04/2023
Analyse the results if willing, with a mathematical discussion | 2023-04-27 | MEDIUM | JOSH MARFLEET | Compare the results prior the fixes and after | TO BE DONE | 26/04/2023 - 27/04/2023
Compare these results with other possible solutions | 2023-04-28 | MEDIUM | JOSH MARFLEET | Analyse the results if willing, with a mathematical discussion | TO BE DONE | 27/04/2023 - 28/04/2023
Contingency Time (7 days) | 2023-05-05 | LOW | JOSH MARFLEET |  | TO BE DONE | 28/04/2023 - 05/05/2023
Solution Review Milestone | 2023-05-05 | HIGH | CHARLIE JACK |  | TO BE DONE | 18/04/2023 - 05/05/2023
Read the Solution Review Specification from the assignment brief | 2023-04-18 | HIGH | CHARLIE JACK |  | TO BE DONE | 18/04/2023 - 18/04/2023
Identify multiple suitable comparisons of your solution by e.g. finding articles | 2023-04-22 | HIGH | CHARLIE JACK | Identify multiple suitable comparisons of your solution by e.g. finding articles | TO BE DONE | 18/04/2023 - 22/04/2023
Explain why they are a fair/unfair comparison for your solution | 2023-04-23 | HIGH | CHARLIE JACK |  | TO BE DONE | 22/04/2023 - 23/04/2023
Discuss the key similarities between the comparison and your solution | 2023-04-24 | HIGH | CHARLIE JACK | Identify multiple suitable comparisons of your solution by e.g. finding articles | TO BE DONE | 23/04/2023 - 24/04/2023
Discuss the key differences between the comparison and your solution | 2023-04-24 | HIGH | CHARLIE JACK | Identify multiple suitable comparisons of your solution by e.g. finding articles | TO BE DONE | 23/04/2023 - 24/04/2023
Ensure the comparison leads to a novel insight | 2023-04-24 | HIGH | CHARLIE JACK |  | TO BE DONE | 23/04/2023 - 24/04/2023
Make recommendations for your solution based on the comparisons | 2023-04-26 | HIGH | CHARLIE JACK |  | TO BE DONE | 24/04/2023 - 26/04/2023
Ensure the presentation and explanations are clear | 2023-04-28 | MEDIUM | CHARLIE JACK | Identify multiple suitable comparisons of your solution by e.g. finding articles | TO BE DONE | 26/04/2023 - 28/04/2023
Contingency Time (7 days) | 2023-05-05 | LOW | CHARLIE JACK |  | TO BE DONE | 28/04/2023 - 05/05/2023
Hand-In Milestone | 2023-05-08 | HIGH | ALL |  | TO BE DONE | 07/05/2023 - 08/05/2023
Ensure document is completed & refined if necessary | 2023-05-07 | HIGH | ALL |  | TO BE DONE | 07/05/2023 - 07/05/2023
Hand in document | 2023-05-08 | HIGH | ALL | Ensure document is completed | TO BE DONE | 07/05/2023 - 08/05/2023
Project Management Documentation Milestone | 2023-05-08 | HIGH | PAWEL LASOTA |  | IN PROGRESS | 07/02/2023 - 08/05/2023
View the Project Management Specification | 2023-02-07 | HIGH | PAWEL LASOTA |  | DONE | 07/02/2023 - 07/02/2023
Gain a basic understanding of what is required | 2023-02-07 | HIGH | PAWEL LASOTA | View the Project Management Specification | DONE | 07/02/2023 - 07/02/2023
Research examples of code of conduct documents | 2023-02-10 | MEDIUM | PAWEL LASOTA |  | DONE | 07/02/2023 - 10/02/2023
Create a code of conduct document stating guidelines & rules within the team | 2023-02-15 | HIGH | PAWEL LASOTA | Research examples of code of conduct documents | DONE | 10/02/2023 - 15/02/2023
Ensure the document is signed by all team members | 2023-02-17 | HIGH | PAWEL LASOTA | Create a code of conduct document stating guidelines & rules within the team | DONE | 15/02/2023 - 17/02/2023
Code of conduct contingency time (1 day) | 2023-02-18 | LOW | PAWEL LASOTA |  | DONE | 17/02/2023 - 18/02/2023
Research examples of risk analysis documents | 2023-02-18 | HIGH | PAWEL LASOTA |  | DONE | 17/02/2023 - 18/02/2023
Create a document with a table with the risk, probability, severity and resolve | 2023-02-19 | HIGH | PAWEL LASOTA | Research examples of risk analysis documents | DONE | 18/02/2023 - 19/02/2023
List possible risks that could happen in the project | 2023-02-21 | HIGH | PAWEL LASOTA | Create a document with a table with the risk, probability, severity and resolve | DONE | 19/02/2023 - 21/02/2023
Judge the probabilities of all risks | 2023-02-23 | HIGH | PAWEL LASOTA | List possible risks that could happen in the project | DONE | 21/02/2023 - 23/02/2023
Judge the severities of all risks | 2023-02-25 | HIGH | PAWEL LASOTA | Judge the probabilities of all risks AND List possible risks that could happen in the project | DONE | 23/02/2023 - 25/02/2023
Describe different ways that these risks could be avoided or resolved | 2023-02-27 | HIGH | PAWEL LASOTA | List possible risks that could happen in the project | DONE | 25/02/2023 - 27/02/2023
Document the progress | 2023-05-05 | HIGH | PAWEL LASOTA |  | DONE | 01/05/2023 - 05/05/2023
Document the communication including meetings | 2023-05-05 | HIGH | PAWEL LASOTA |  | IN PROGRESS | 05/05/2023 - 05/05/2023
Document different project management practices | 2023-05-06 | HIGH | PAWEL LASOTA |  | IN PROGRESS | 05/05/2023 - 06/05/2023
Justify project management practices with documentation | 2023-05-06 | MEDIUM | PAWEL LASOTA | Document different project management practices | IN PROGRESS | 06/05/2023 - 06/05/2023
Contingency Time (2 days) | 2023-05-08 | LOW | PAWEL LASOTA |  | TO BE DONE | 06/05/2023 - 08/05/2023

## GANTT CHART
DILSTON SOFTWARE ENGINEERING PRACTICE GANTT CHART
[7 empty] | WEEK 1 | [6 empty] | WEEK 2 | [6 empty] | WEEK 3 | [6 empty] | WEEK 4 | [6 empty] | WEEK 5 | [6 empty] | WEEK 6 | [6 empty] | WEEK 7 | [6 empty] | WEEK 8 | [6 empty] | WEEK 9 | [6 empty] | WEEK 10 | [6 empty] | WEEK 11 | [6 empty] | WEEK 12 | [6 empty] | WEEK 13 | [6 empty] | WEEK 14
[8 empty] | 1-7 FEB | [6 empty] | 8-14 FEB | [6 empty] | 15-21 FEB | [6 empty] | 22-28 FEB | [6 empty] | 1-7 MAR | [6 empty] | 8-14 MAR | [6 empty] | 15-21 MAR | [6 empty] | 22-28 MAR | [6 empty] | 29 MAR - 4 APR | [6 empty] | 5-11 APR | [6 empty] | 12-18 APR | [6 empty] | 19-25 APR | [6 empty] | 26 APR - 2 MAY | [6 empty] | 3-9 MAY
[5 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9
[5 empty] | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T
Task | Lead | Timeline | Status | Days
Skills Audit & Proposal Milestone | ALL | 01/02/2023 - 17/02/2023 | DONE | 17
View the skills audit template | ALL | 01/02/2023 - 06/02/2023 | DONE | 6 | bar: 1 W to 1-7 FEB 6 M
Ensure all team members fill out their section of the skills audit | ALL | 06/02/2023 - 10/02/2023 | DONE | 4 | bar: 1-7 FEB 6 M to 1-7 FEB 10 F
Fill out the team strengths & weaknesses at bottom of skills audit | PAWEL LASOTA | 10/02/2023 - 12/02/2023 | DONE | 2 | bar: 1-7 FEB 10 F to 8-14 FEB 12 S
Fill out project manager comments on the team at bottom of skills audit | PAWEL LASOTA | 10/02/2023 - 12/02/2023 | DONE | 2 | bar: 1-7 FEB 10 F to 8-14 FEB 12 S
Chat with team about the project idea & proposal | ALL | 12/02/2023 - 13/02/2023 | DONE | 1 | bar: 8-14 FEB 12 S to 8-14 FEB 13 M
Upon team agreement upon project idea, fill out the proposal section | PAWEL LASOTA | 13/02/2023 - 14/02/2023 | DONE | 1 | bar: 8-14 FEB 13 M to 8-14 FEB 14 T
Ensure the skills audit is completed | PAWEL LASOTA | 14/02/2023 - 15/02/2023 | DONE | 1 | bar: 8-14 FEB 14 T to 8-14 FEB 15 W
Hand in the skills audit | PAWEL LASOTA | 15/02/2023 - 16/02/2023 | DONE | 1 | bar: 8-14 FEB 15 W to 8-14 FEB 16 T
Skills audit contingency (1 days) | ALL | 16/02/2023 - 17/02/2023 | DONE | 1 | bar: 8-14 FEB 16 T to 8-14 FEB 17 F
Organising Team Meetings/Communication Milestone | PAWEL LASOTA | 07/02/2023 - 16/02/2023 | DONE | 9
Find out availability from each member | PAWEL LASOTA | 07/02/2023 - 08/02/2023 | DONE | 1 | bar: 1-7 FEB 7 T to 1-7 FEB 8 W
Plan regular weekly meetings that match availability | PAWEL LASOTA | 08/02/2023 - 11/02/2023 | DONE | 3 | bar: 1-7 FEB 8 W to 8-14 FEB 11 S
Ask all team members whether they are happy communicating with Discord | PAWEL LASOTA | 11/02/2023 - 14/02/2023 | DONE | 3 | bar: 8-14 FEB 11 S to 8-14 FEB 14 T
Contingency Time (2 days) | PAWEL LASOTA | 14/02/2023 - 16/02/2023 | DONE | 2 | bar: 8-14 FEB 14 T to 8-14 FEB 16 T
Project Management Documentation Milestone | PAWEL LASOTA | 07/02/2023 - 08/05/2023 | IN PROGRESS | 30
View the Project Management Specification | PAWEL LASOTA | 07/02/2023 - 07/02/2023 | DONE | 1 | bar: 1-7 FEB 7 T
Gain a basic understanding of what is required | PAWEL LASOTA | 07/02/2023 - 07/02/2023 | DONE | 1 | bar: 1-7 FEB 7 T
Research examples of code of conduct documents | PAWEL LASOTA | 07/02/2023 - 10/02/2023 | DONE | 3 | bar: 1-7 FEB 7 T to 1-7 FEB 10 F
Create a code of conduct document stating guidelines & rules within the team | PAWEL LASOTA | 10/02/2023 - 15/02/2023 | DONE | 5 | bar: 1-7 FEB 10 F to 8-14 FEB 15 W
Ensure the document is signed by all team members | PAWEL LASOTA | 15/02/2023 - 17/02/2023 | DONE | 2 | bar: 8-14 FEB 15 W to 8-14 FEB 17 F
Code of conduct contingency time (1 day) | PAWEL LASOTA | 17/02/2023 - 18/02/2023 | DONE | 1 | bar: 8-14 FEB 17 F to 15-21 FEB 18 S
Research examples of risk analysis documents | PAWEL LASOTA | 17/02/2023 - 18/02/2023 | DONE | 1 | bar: 8-14 FEB 17 F to 15-21 FEB 18 S
Create a document with a table with the risk, probability, severity and resolve | PAWEL LASOTA | 18/02/2023 - 19/02/2023 | DONE | 1 | bar: 15-21 FEB 18 S to 15-21 FEB 19 S
List possible risks that could happen in the project | PAWEL LASOTA | 19/02/2023 - 21/02/2023 | DONE | 2 | bar: 15-21 FEB 19 S to 15-21 FEB 21 T
Judge the probabilities of all risks | PAWEL LASOTA | 21/02/2023 - 23/02/2023 | DONE | 2 | bar: 15-21 FEB 21 T to 15-21 FEB 23 T
Judge the severities of all risks | PAWEL LASOTA | 23/02/2023 - 25/02/2023 | DONE | 2 | bar: 15-21 FEB 23 T to 22-28 FEB 25 S
Describe different ways that these risks could be avoided or resolved | PAWEL LASOTA | 25/02/2023 - 27/02/2023 | DONE | 2 | bar: 22-28 FEB 25 S to 22-28 FEB 27 M
Document the progress | PAWEL LASOTA | 01/05/2023 - 05/05/2023 | TO BE DONE | 4 | bar: 26 APR - 2 MAY 1 M to 26 APR - 2 MAY 5 F
Document the communication including meetings | PAWEL LASOTA | 05/05/2023 - 05/05/2023 | TO BE DONE | 1 | bar: 26 APR - 2 MAY 5 F
Document different project management practices | PAWEL LASOTA | 05/05/2023 - 06/05/2023 | TO BE DONE | 1 | bar: 26 APR - 2 MAY 5 F to 3-9 MAY 6 S
Justify project management practices with documentation | PAWEL LASOTA | 06/05/2023 - 06/05/2023 | TO BE DONE | 1 | bar: 3-9 MAY 6 S
Contingency Time (2 days) | PAWEL LASOTA | 06/05/2023 - 08/05/2023 | TO BE DONE | 2 | bar: 3-9 MAY 6 S to 3-9 MAY 8 M
Solution Design Milestone | JOSH MARFLEET | 10/02/2023 - 22/03/2023 | IN PROGRESS | 40
View the Solution Design Specification brief | JOSH MARFLEET | 10/02/2023 - 10/02/2023 | DONE | 0.5 | bar: 1-7 FEB 10 F
Research examples of solution designing online | JOSH MARFLEET | 10/02/2023 - 10/02/2023 | DONE | 0.5 | bar: 1-7 FEB 10 F
Create a draw.io page | JOSH MARFLEET | 10/02/2023 - 11/02/2023 | DONE | 1 | bar: 1-7 FEB 10 F to 8-14 FEB 11 S
Plot a flowchart of what the project will look like step by step | JOSH MARFLEET | 11/02/2023 - 11/02/2023 | DONE | 0.5 | bar: 8-14 FEB 11 S
Implement the flowchart into a word document | JOSH MARFLEET | 11/02/2023 - 20/02/2023 | DONE | 8 | bar: 8-14 FEB 11 S to 15-21 FEB 20 M
Create a solution description | JOSH MARFLEET | 20/02/2023 - 21/02/2023 | DONE | 1 | bar: 15-21 FEB 20 M to 15-21 FEB 21 T
Describe the functionality of the solution | JOSH MARFLEET | 21/02/2023 - 22/02/2023 | DONE | 1 | bar: 15-21 FEB 21 T to 15-21 FEB 22 W
Create a data description of what kind of data will be used | JOSH MARFLEET | 22/02/2023 - 28/02/2023 | DONE | 5.5 | bar: 15-21 FEB 22 W to 22-28 FEB 28 T
Explain why we will use this data | JOSH MARFLEET | 28/02/2023 - 05/03/2023 | IN PROGRESS | 5 | bar: 22-28 FEB 28 T to 1-7 MAR 5 S
Discuss the solution motivation | JOSH MARFLEET | 05/03/2023 - 10/03/2023 | IN PROGRESS | 5 | bar: 1-7 MAR 5 S to 1-7 MAR 10 F
Explain why we decided to do this project | JOSH MARFLEET | 10/03/2023 - 15/03/2023 | IN PROGRESS | 5 | bar: 1-7 MAR 10 F to 8-14 MAR 15 W
Contingency Time (7 days) | JOSH MARFLEET | 15/03/2023 - 22/03/2023 | TO BE DONE | 7 | bar: 8-14 MAR 15 W to 15-21 MAR 22 W
Baseline Implementation Milestone | JACK WELCH | 10/02/2023 - 27/03/2023 | DONE | 44
Create a new python project using pyCharm named Face_Recognition | JACK WELCH | 10/02/2023 - 10/02/2023 | DONE | 0.5 | bar: 1-7 FEB 10 F
Create an environment via anaconda for this project | JACK WELCH | 10/02/2023 - 10/02/2023 | DONE | 0.5 | bar: 1-7 FEB 10 F
Find a pre-built face recognition library | JACK WELCH | 10/02/2023 - 13/02/2023 | DONE | 2.5 | bar: 1-7 FEB 10 F to 8-14 FEB 13 M
Download all necessary libraries | JACK WELCH | 13/02/2023 - 13/02/2023 | DONE | 0.5 | bar: 8-14 FEB 13 M
Connect the pyCharm project to github for easy collaboration | JACK WELCH | 13/02/2023 - 14/02/2023 | DONE | 1 | bar: 8-14 FEB 13 M to 8-14 FEB 14 T
Test the project can be collaborated/viewed with via github | JACK WELCH | 14/02/2023 - 14/02/2023 | DONE | 0.5 | bar: 8-14 FEB 14 T
Import the necessary libraries | JACK WELCH | 14/02/2023 - 15/02/2023 | DONE | 1 | bar: 8-14 FEB 14 T to 8-14 FEB 15 W
Find a dataset for baseline | JACK WELCH | 15/02/2023 - 20/02/2023 | DONE | 4.5 | bar: 8-14 FEB 15 W to 15-21 FEB 20 M
Ensure the dataset is in the correct format - subfolders with class names | JACK WELCH | 20/02/2023 - 20/02/2023 | DONE | 0.5 | bar: 15-21 FEB 20 M
Ensure each class/person has enough images to train on | JACK WELCH | 20/02/2023 - 20/02/2023 | DONE | 0.5 | bar: 15-21 FEB 20 M
Program a face detection/extraction algorithm | JACK WELCH | 20/02/2023 - 02/03/2023 | DONE | 8.5 | bar: 15-21 FEB 20 M to 22-28 FEB 2 T
Program the recognition aspect using the dataset | JACK WELCH | 02/03/2023 - 10/03/2023 | DONE | 7.5 | bar: 22-28 FEB 2 T to 1-7 MAR 10 F
Program the webcam so that the app opens it | JACK WELCH | 10/03/2023 - 12/03/2023 | DONE | 2 | bar: 1-7 MAR 10 F to 8-14 MAR 12 S
Program the face detection into the webcam | JACK WELCH | 12/03/2023 - 15/03/2023 | DONE | 2.5 | bar: 8-14 MAR 12 S to 8-14 MAR 15 W
Program the face recognition into the webcam | JACK WELCH | 15/03/2023 - 15/03/2023 | DONE | 0.5 | bar: 8-14 MAR 15 W
Evaluate the solution | JACK WELCH | 16/03/2023 - 20/03/2023 | DONE | 4 | bar: 8-14 MAR 16 T to 15-21 MAR 20 M
Contingency Time (7 days) | JACK WELCH | 20/03/2023 - 27/03/2023 | DONE | 7 | bar: 15-21 MAR 20 M to 22-28 MAR 27 M
User Interface Milestone | CHARLIE JACK | 10/02/2023 - 27/03/2023 | IN PROGRESS | 45
Read the UI specification from the assignment brief | CHARLIE JACK | 10/02/2023 - 10/02/2023 | DONE | 0.5 | bar: 1-7 FEB 10 F
Research relevant examples of UI for face recognition | CHARLIE JACK | 10/02/2023 - 11/02/2023 | DONE | 1 | bar: 1-7 FEB 10 F to 8-14 FEB 11 S
Find a good UI software for integration | CHARLIE JACK | 11/02/2023 - 11/02/2023 | DONE | 0.5 | bar: 8-14 FEB 11 S
Find a tutorial on how to use the software and learn it a little | CHARLIE JACK | 11/02/2023 - 20/02/2023 | DONE | 9 | bar: 8-14 FEB 11 S to 15-21 FEB 20 M
Communicate with others on the vision of the application to provide good UI | CHARLIE JACK | 20/02/2023 - 21/02/2023 | DONE | 1 | bar: 15-21 FEB 20 M to 15-21 FEB 21 T
Design the UI using low fidelity prototyping | CHARLIE JACK | 21/02/2023 - 23/02/2023 | DONE | 2 | bar: 15-21 FEB 21 T to 15-21 FEB 23 T
Design the UI using high fidelity prototyping | CHARLIE JACK | 23/02/2023 - 26/02/2023 | DONE | 3 | bar: 15-21 FEB 23 T to 22-28 FEB 26 S
Create justifications for why the design is being designed this way | CHARLIE JACK | 26/02/2023 - 27/02/2023 | DONE | 1 | bar: 22-28 FEB 26 S to 22-28 FEB 27 M
Communicate with others about the designs | CHARLIE JACK | 27/02/2023 - 28/02/2023 | DONE | 1 | bar: 22-28 FEB 27 M to 22-28 FEB 28 T
Ensure the designs show signs of ease of use | CHARLIE JACK | 28/02/2023 - 02/03/2023 | IN PROGRESS | 2 | bar: 22-28 FEB 28 T to 22-28 FEB 2 T
Integrate the design into a programming software | CHARLIE JACK | 02/03/2023 - 10/03/2023 | IN PROGRESS | 8 | bar: 22-28 FEB 2 T to 1-7 MAR 10 F
Program relevant buttons and other interactions | CHARLIE JACK | 10/03/2023 - 15/03/2023 | TO BE DONE | 5 | bar: 1-7 MAR 10 F to 8-14 MAR 15 W
Test the interaction yourself and with the team to ensure good interactivity | CHARLIE JACK | 15/03/2023 - 17/03/2023 | TO BE DONE | 1.5 | bar: 8-14 MAR 15 W to 8-14 MAR 17 F
Log the tests to show progress of improvements | CHARLIE JACK | 17/03/2023 - 18/03/2023 | TO BE DONE | 1 | bar: 8-14 MAR 17 F to 15-21 MAR 18 S
Discuss the testing and justify any changes made | CHARLIE JACK | 18/03/2023 - 20/03/2023 | TO BE DONE | 1.5 | bar: 15-21 MAR 18 S to 15-21 MAR 20 M
Contingency Time (7 days) | CHARLIE JACK | 20/03/2023 - 27/03/2023 | TO BE DONE | 7 | bar: 15-21 MAR 20 M to 22-28 MAR 27 M
Project Ideation Milestone | PAWEL LASOTA | 10/02/2023 - 27/03/2023 | IN PROGRESS
Start writing up a problem statement | PAWEL LASOTA | 10/02/2023 - 10/02/2023 | DONE | bar: 1-7 FEB 10 F
In the project statement, state the idea and issue at hand | PAWEL LASOTA | 10/02/2023 - 10/02/2023 | DONE | bar: 1-7 FEB 10 F
Start writing up the problem motivation | PAWEL LASOTA | 10/02/2023 - 11/02/2023 | DONE | bar: 1-7 FEB 10 F to 8-14 FEB 11 S
In the problem motivation, state why we're doing what we're doing | PAWEL LASOTA | 11/02/2023 - 11/02/2023 | DONE | bar: 8-14 FEB 11 S
Start thinking about the Literature Review for different solutions | PAWEL LASOTA | 11/02/2023 - 12/02/2023 | DONE | bar: 8-14 FEB 11 S to 8-14 FEB 12 S
Research existing solutions to face recognition | PAWEL LASOTA | 12/02/2023 - 13/02/2023 | DONE | bar: 8-14 FEB 12 S to 8-14 FEB 13 M
Identify the face recognition techniques these solutions have used | PAWEL LASOTA | 13/02/2023 - 14/02/2023 | DONE | bar: 8-14 FEB 13 M to 8-14 FEB 14 T
Find multiple techniques | PAWEL LASOTA | 13/02/2023 - 14/02/2023 | DONE | bar: 8-14 FEB 13 M to 8-14 FEB 14 T
Explain using references what the techniques consists of | PAWEL LASOTA | 14/02/2023 - 15/03/2023 | IN PROGRESS | bar: 8-14 FEB 14 T to 8-14 MAR 15 W
Identify the strengths of each technique | PAWEL LASOTA | 14/02/2023 - 15/03/2023 | IN PROGRESS | bar: 8-14 FEB 14 T to 8-14 MAR 15 W
Identify the weaknessess of each technique | PAWEL LASOTA | 14/02/2023 - 15/03/2023 | IN PROGRESS | bar: 8-14 FEB 14 T to 8-14 MAR 15 W
Write up the technique, strengths and weaknesses | PAWEL LASOTA | 14/02/2023 - 15/03/2023 | IN PROGRESS | bar: 8-14 FEB 14 T to 8-14 MAR 15 W
Compare the techniques and identify which one is better in which scenario | PAWEL LASOTA | 14/02/2023 - 15/03/2023 | TO BE DONE | bar: 8-14 FEB 14 T to 8-14 MAR 15 W
Write up a conclusion as a takeaway for the reader | PAWEL LASOTA | 14/02/2023 - 15/03/2023 | TO BE DONE | bar: 8-14 FEB 14 T to 8-14 MAR 15 W
Write up a project statement | PAWEL LASOTA | 15/03/2023 - 20/03/2023 | TO BE DONE | bar: 8-14 MAR 15 W to 15-21 MAR 20 M
Contingency Time (7 days) | PAWEL LASOTA | 20/03/2023 - 27/03/2023 | TO BE DONE | bar: 15-21 MAR 20 M to 22-28 MAR 27 M
Ethical Evaluation Milestone | JOSH MARFLEET | 18/04/2023 - 05/05/2023 | TO BE DONE
Read the Ethical Evaluation Specification from the assignment brief | JOSH MARFLEET | 18/04/2023 - 18/04/2023 | TO BE DONE | bar: 12-18 APR 18 T
Read into bias analysis on the internet | JOSH MARFLEET | 18/04/2023 - 19/04/2023 | TO BE DONE | bar: 12-18 APR 18 T to 12-18 APR 19 W
Discuss input data used in the model | JOSH MARFLEET | 18/04/2023 - 19/04/2023 | TO BE DONE | bar: 12-18 APR 18 T to 12-18 APR 19 W
Discuss how this input data is augmentated and how it prevents bias | JOSH MARFLEET | 19/04/2023 - 20/04/2023 | TO BE DONE | bar: 12-18 APR 19 W to 12-18 APR 20 T
Discuss how the data is normalised to prevent bias | JOSH MARFLEET | 19/04/2023 - 20/04/2023 | TO BE DONE | bar: 12-18 APR 19 W to 12-18 APR 20 T
Discuss any other techniques that are used that could potentially prevent bias | JOSH MARFLEET | 19/04/2023 - 20/04/2023 | TO BE DONE | bar: 12-18 APR 19 W to 12-18 APR 20 T
Discuss any improvements into the solution that could further prevent bias | JOSH MARFLEET | 20/04/2023 - 21/04/2023 | TO BE DONE | bar: 12-18 APR 20 T to 12-18 APR 21 F
Discuss why preventing bias is important | JOSH MARFLEET | 20/04/2023 - 21/04/2023 | TO BE DONE | bar: 12-18 APR 20 T to 12-18 APR 21 F
Read into common ethical issues in face recognition | JOSH MARFLEET | 20/04/2023 - 21/04/2023 | TO BE DONE | bar: 12-18 APR 20 T to 12-18 APR 21 F
Write about multiple of these ethical issues you have researched | JOSH MARFLEET | 20/04/2023 - 21/04/2023 | TO BE DONE | bar: 12-18 APR 20 T to 12-18 APR 21 F
Write why ethics is important to discuss | JOSH MARFLEET | 21/04/2023 - 22/04/2023 | TO BE DONE | bar: 12-18 APR 21 F to 19-25 APR 22 S
Give examples of ethical problems other solutions have experienced in face recognition and the consequences | JOSH MARFLEET | 21/04/2023 - 22/04/2023 | TO BE DONE | bar: 12-18 APR 21 F to 19-25 APR 22 S
Look into the solution and identify ethical problems | JOSH MARFLEET | 21/04/2023 - 22/04/2023 | TO BE DONE | bar: 12-18 APR 21 F to 19-25 APR 22 S
If possible, fix these identified problems - If willing, incorporate state-of-the-art third party tools to correct model bias | JOSH MARFLEET | 22/04/2023 - 25/04/2023 | TO BE DONE | bar: 19-25 APR 22 S to 19-25 APR 25 T
Discuss the identified problems and the fixes | JOSH MARFLEET | 22/04/2023 - 25/04/2023 | TO BE DONE | bar: 19-25 APR 22 S to 19-25 APR 25 T
Compare the results prior the fixes and after | JOSH MARFLEET | 25/04/2023 - 26/04/2023 | TO BE DONE | bar: 19-25 APR 25 T to 19-25 APR 26 W
Analyse the results if willing, with a mathematical discussion | JOSH MARFLEET | 26/04/2023 - 27/04/2023 | TO BE DONE | bar: 19-25 APR 26 W to 19-25 APR 27 T
Compare these results with other possible solutions | JOSH MARFLEET | 27/04/2023 - 28/04/2023 | TO BE DONE | bar: 19-25 APR 27 T to 19-25 APR 28 F
Contingency Time (7 days) | JOSH MARFLEET | 28/04/2023 - 05/05/2023 | TO BE DONE | bar: 19-25 APR 28 F to 26 APR - 2 MAY 5 F
Solution Review Milestone | CHARLIE JACK | 18/04/2023 - 05/05/2023 | TO BE DONE
Read the Solution Review Specification from the assignment brief | CHARLIE JACK | 18/04/2023 - 18/04/2023 | TO BE DONE | bar: 12-18 APR 18 T
Identify multiple suitable comparisons of your solution by e.g. finding articles | CHARLIE JACK | 18/04/2023 - 22/04/2023 | TO BE DONE | bar: 12-18 APR 18 T to 19-25 APR 22 S
Explain why they are a fair/unfair comparison for your solution | CHARLIE JACK | 22/04/2023 - 23/04/2023 | TO BE DONE
Discuss the key similarities between the comparison and your solution | CHARLIE JACK | 23/04/2023 - 24/04/2023 | TO BE DONE
Discuss the key differences between the comparison and your solution | CHARLIE JACK | 23/04/2023 - 24/04/2023 | TO BE DONE
Ensure the comparison leads to a novel insight | CHARLIE JACK | 23/04/2023 - 24/04/2023 | TO BE DONE
Make recommendations for your solution based on the comparisons | CHARLIE JACK | 24/04/2023 - 26/04/2023 | TO BE DONE
Ensure the presentation and explanations are clear | CHARLIE JACK | 26/04/2023 - 28/04/2023 | TO BE DONE
Contingency Time (7 days) | CHARLIE JACK | 28/04/2023 - 05/05/2023 | TO BE DONE
Solution Testing Milestone | JACK WELCH | 18/04/2023 - 05/05/2023 | TO BE DONE
Read the Solution Testing specification from the assignment brief | JACK WELCH | 18/04/2023 - 18/04/2023 | TO BE DONE
Create a word document with a table for a test plan | JACK WELCH | 18/04/2023 - 19/04/2023 | TO BE DONE
The headings of the table should involve what you are going to test and results | JACK WELCH | 18/04/2023 - 19/04/2023 | TO BE DONE
Create test cases for identifying flaws | JACK WELCH | 18/04/2023 - 19/04/2023 | TO BE DONE
Write the test cases into the table | JACK WELCH | 18/04/2023 - 19/04/2023 | TO BE DONE
Perform required tests on all of these test cases | JACK WELCH | 19/04/2023 - 23/04/2023 | TO BE DONE
Write down what you have found regarding these tests | JACK WELCH | 19/04/2023 - 23/04/2023 | TO BE DONE
Create a report discussing your findings | JACK WELCH | 19/04/2023 - 23/04/2023 | TO BE DONE
Discuss your recommendations based on the results | JACK WELCH | 19/04/2023 - 23/04/2023 | TO BE DONE
Ensure your justification is worthwile and suitable for purpose | JACK WELCH | 19/04/2023 - 23/04/2023 | TO BE DONE
Ensure your recommendations will help improve the system | JACK WELCH | 19/04/2023 - 23/04/2023 | TO BE DONE
Ensure the document is clear and results are well analysed | JACK WELCH | 19/04/2023 - 23/04/2023 | TO BE DONE
Perform further tests that will have a purpose of confusing the model | JACK WELCH | 23/04/2023 - 27/04/2023 | TO BE DONE
Discuss your findings in the document about these further tests | JACK WELCH | 23/04/2023 - 27/04/2023 | TO BE DONE
Discuss your recommendations on improving the model itself | JACK WELCH | 23/04/2023 - 27/04/2023 | TO BE DONE
Finalise your discussion with a conclusion summarising the tests | JACK WELCH | 27/04/2023 - 28/04/2023 | TO BE DONE
Contingency Time (7 days) | JACK WELCH | 28/04/2023 - 05/05/2023 | TO BE DONE
Hand-In Milestone | ALL | 07/05/2023 - 08/05/2023 | TO BE DONE
Ensure document is completed & refined if necessary | ALL | 07/05/2023 - 07/05/2023 | TO BE DONE
Hand in document | ALL | 07/05/2023 - 08/05/2023 | TO BE DONE
Iterative Development (Team) Milestone | ALL | 23/03/2023 - 25/04/2023 | TO BE DONE
All members to read & understand the iterative development specification | ALL | 23/03/2023 - 24/03/2023 | TO BE DONE
Look online for face recognition examples | ALL | 23/03/2023 - 24/03/2023 | TO BE DONE
Find a small faces dataset that will be used for training the solution | ALL | 23/03/2023 - 24/03/2023 | TO BE DONE
Using the same environment as in baseline, import necessary libraries | ALL | 23/03/2023 - 24/03/2023 | TO BE DONE
Implement code to access the dataset | ALL | 24/03/2023 - 25/03/2023 | TO BE DONE
Normalise the dataset | ALL | 24/03/2023 - 25/03/2023 | TO BE DONE
Resize the dataset so all images are the same size | ALL | 24/03/2023 - 25/03/2023 | TO BE DONE
Augment the data by e.g. tilting the images | ALL | 24/03/2023 - 25/03/2023 | TO BE DONE
Implement code to split the training and testing data with a ratio of 80:20 | ALL | 24/03/2023 - 25/03/2023 | TO BE DONE
Extract/detect the faces in all images | ALL | 25/03/2023 - 26/03/2023 | TO BE DONE
Implement a CNN sequential model (Mini-Milestone) | ALL | 26/03/2023 - 28/03/2023 | TO BE DONE
Create multiple convolutional (Conv2D) layers | ALL | 26/03/2023 - 27/03/2023 | TO BE DONE
Specify the number of filters, kernel_size, activation methods, input shapes | ALL | 26/03/2023 - 27/03/2023 | TO BE DONE
Create multiple MaxPooling2D layers | ALL | 26/03/2023 - 27/03/2023 | TO BE DONE
Specify the pool size of each max pooling layer | ALL | 26/03/2023 - 27/03/2023 | TO BE DONE
Implement a Flatten function | ALL | 27/03/2023 - 28/03/2023 | TO BE DONE
Create multiple Dense layers with a relu activation | ALL | 27/03/2023 - 28/03/2023 | TO BE DONE
Implemet multiple dropouts of around 0.5 to prevent overfitting | ALL | 27/03/2023 - 28/03/2023 | TO BE DONE
Compile the CNN model | ALL | 27/03/2023 - 28/03/2023 | TO BE DONE
Train the CNN model using model.fit function | ALL | 28/03/2023 - 29/03/2023 | TO BE DONE
Specify the batch size, epochs, steps_per_epoch, training and validation data | ALL | 28/03/2023 - 29/03/2023 | TO BE DONE
Evaluate the model via a graph with accuracy as y label and epoch as x label | ALL | 29/03/2023 - 30/03/2023 | TO BE DONE
Evaluate the model via a graph with model loss as y being loss and x being epoch | ALL | 29/03/2023 - 30/03/2023 | TO BE DONE
Using the model use the .predict() function to predict test data based on training data | ALL | 29/03/2023 - 30/03/2023 | TO BE DONE
Create a confusion matrix | ALL | 30/03/2023 - 31/03/2023 | TO BE DONE
Calculate the accuracy based on the confusion matrix | ALL | 30/03/2023 - 31/03/2023 | TO BE DONE
Implement code to access the webcam (Mini-Milestone) | ALL | 31/03/2023 - 01/04/2023 | TO BE DONE
Implement code for validation whether webcam is available | ALL | 31/03/2023 - 31/03/2023 | TO BE DONE
Implement code to capture each frame of the webcam | ALL | 31/03/2023 - 31/03/2023 | TO BE DONE
Convert each frame to grayscale | ALL | 31/03/2023 - 31/03/2023 | TO BE DONE
Detect faces within the frame based on the feature extraction methodology | ALL | 01/04/2023 - 01/04/2023 | TO BE DONE
Implement a for loop for each frame to convert to gray and resize face to required dimensions | ALL | 01/04/2023 - 01/04/2023 | TO BE DONE
Predict the face using the model | ALL | 01/04/2023 - 01/04/2023 | TO BE DONE
Calculate the confidence and display it | ALL | 01/04/2023 - 01/04/2023 | TO BE DONE
Create a confidence threshold with over 90 being confident enough to predict | ALL | 01/04/2023 - 01/04/2023 | TO BE DONE
Else, the confidence under 90 will be considered 'unknown' | ALL | 01/04/2023 - 01/04/2023 | TO BE DONE
Display the frame | ALL | 01/04/2023 - 01/04/2023 | TO BE DONE
Use other novel pre-processing techniques and test the accuracy again | ALL | 01/04/2023 - 04/04/2023 | TO BE DONE
Change the CNN model to pre-built CNN models such as resnet for comparison | ALL | 04/04/2023 - 10/04/2023 | TO BE DONE
Change the code accordingly to make the pre-built model work | ALL | 04/04/2023 - 10/04/2023 | TO BE DONE
Test the accuracy with at least one other model | ALL | 04/04/2023 - 10/04/2023 | TO BE DONE
Write down the impact of changing pre-processing of data methodologies on the accuracy | ALL | 10/04/2023 - 11/04/2023 | TO BE DONE
Compare & Evaluate different pre-processing techniques in a document | ALL | 11/04/2023 - 13/04/2023 | TO BE DONE
Write down the impact of changing the CNN model to pre-built CNN models | ALL | 11/04/2023 - 13/04/2023 | TO BE DONE
Compare & Evaluate the different models and comparisons | ALL | 13/04/2023 - 15/04/2023 | TO BE DONE
Tune parameters for each model to see which parameters are best | ALL | 15/04/2023 - 17/04/2023 | TO BE DONE
Document and justify the changes for parameters, e.g. better accuracy | ALL | 15/04/2023 - 17/04/2023 | TO BE DONE
Implement an appendix in the word document with code | ALL | 17/04/2023 - 18/04/2023 | TO BE DONE
Ensure the work is well documented and results well organised | ALL | 17/04/2023 - 18/04/2023 | TO BE DONE
Contingency Time (7 days) | ALL | 18/04/2023 - 25/04/2023 | TO BE DONE

## KEY
Status | STATUS | MEMBERS
DONE | HIGH | PAWEL LASOTA
IN PROGRESS | MEDIUM | JACK WELCH
TO BE DONE | LOW | CHARLIE JACK
STUCK |  | JOSH MARFLEET
ALL