## TASK LIST
DILSTON SOFTWARE ENGINEERING PRACTICE
Task | Deadline | Priority | Person | Dependency | Status | Timeline
Skills Audit & Proposal Milestone | 2023-02-17 | HIGH | ALL |  | DONE | 01/02/2023 - 17/02/2023
View the skills audit template | 2023-02-06 | HIGH | ALL |  | DONE | 01/02/2023 - 06/02/2023
Ensure all team members fill out their section of the skills audit | 2023-02-12 | HIGH | ALL | View the skills audit template | DONE | 06/02/2023 - 12/02/2023
Chat with team about the project idea & proposal | 2023-02-13 | MEDIUM | ALL |  | DONE | 12/02/2023 - 13/02/2023
Upon team agreement upon project idea, fill out the proposal section | 2023-02-14 | HIGH | ALL | Chat with team about the project idea & proposal | DONE | 13/02/2023 - 14/02/2023
Ensure the skills audit is completed | 2023-02-15 | HIGH | ALL | Ensure all team members fill out their section of the skills audit Upon team agreement upon project idea, fill out the proposal section | DONE | 14/02/2023 - 15/02/2023
Hand in the skills audit | 2023-02-16 | HIGH | ALL | Ensure the skills audit is completed | DONE | 15/02/2023 - 16/02/2023
Skills audit contingency (1 days) | 2023-02-17 | LOW | ALL |  | DONE | 16/02/2023 - 17/02/2023
Organising Team Meetings/Communication Milestone | 2023-02-16 | HIGH | ALL |  | DONE | 15/02/2023 - 16/02/2023
Find out availability from each member | 2023-02-15 | HIGH | PAWEL LASOTA |  | DONE | 15/02/2023 - 15/02/2023
Plan regular weekly meetings that match availability | 2023-02-16 | MEDIUM | PAWEL LASOTA | Find out availability from each member | DONE | 16/02/2023 - 16/02/2023
Project Ideation Milestone | 2023-03-02 | HIGH | PAWEL LASOTA |  | TO BE DONE
Research possible solutions
Solution Design Milestone |  |  | JOSH MARFLEET |  | TO BE DONE
Baseline Implementation Milestone |  |  | JACK WELCH |  | IN PROGRESS
Create a new python project using pyCharm named Face_Recognition |  |  | JACK WELCH |  | IN PROGRESS
Create an environment via anaconda for this project |  |  | JACK WELCH | Create a new python project using pyCharm named Face_Recognition | IN PROGRESS
Download all necessary libraries |  |  | JACK WELCH | Create an environment via anaconda for this project | IN PROGRESS
Connect the pyCharm project to github for easy collaboration |  |  | JACK WELCH |  | IN PROGRESS
Test the project can be collaborated with via github |  |  | JACK WELCH | Connect the pyCharm project to github for easy collaboration | IN PROGRESS
Iterative Development (Team) Milestone |  |  | ALL |  | TO BE DONE
Solution Testing Milestone |  |  | JACK WELCH |  | TO BE DONE
User Interface Milestone |  |  | CHARLIE JACK |  | TO BE DONE
Ethical Evaluation Milestone |  |  | JOSH MARFLEET |  | TO BE DONE
Solution Review Milestone |  |  | CHARLIE JACK |  | TO BE DONE
Hand-In Milestone | 2023-05-08 |  | ALL |  | STUCK
Ensure document is completed |  |  | ALL |  | STUCK
Hand in document |  |  | ALL |  | STUCK
Project Management Documentation Milestone | 2023-05-08 | HIGH | PAWEL LASOTA |  | IN PROGRESS | 01/02/2023 - 08/05/2023
View the Project Management Specification | 2023-02-01 | HIGH | PAWEL LASOTA |  | DONE | 01/02/2023 - 01/02/2023
Gain a basic understanding of what is required | 2023-02-01 | HIGH | PAWEL LASOTA | View the Project Management Specification | DONE | 01/02/2023 - 01/02/2023
Research examples of code of conduct documents | 2023-02-01 | MEDIUM | PAWEL LASOTA |  | DONE | 01/02/2023 - 01/02/2023
Create a code of conduct document stating guidelines & rules within the team | 2023-02-02 | HIGH | PAWEL LASOTA | Research examples of code of conduct documents | DONE | 02/02/2023 - 02/02/2023
Ensure the document is signed by all team members | 2023-02-03 | HIGH | PAWEL LASOTA | Create a code of conduct document stating guidelines & rules within the team | DONE | 03/02/2023 - 03/02/2023
Code of conduct contingency time (1 day) | 2023-02-04 | LOW | PAWEL LASOTA |  | DONE | 04/02/2023 - 04/02/2023
Research examples of risk analysis documents | 2023-02-05 | HIGH | PAWEL LASOTA |  | DONE | 05/02/2023 - 05/02/2023
Create a document with a table with the risk, probability, severity and resolve | 2023-02-05 | HIGH | PAWEL LASOTA | Research examples of risk analysis documents | DONE | 05/02/2023 - 05/02/2023
List possible risks that could happen in the project | 2023-02-05 | HIGH | PAWEL LASOTA | Create a document with a table with the risk, probability, severity and resolve | DONE | 05/02/2023 - 05/02/2023
Judge the probabilities of all risks | 2023-02-05 | HIGH | PAWEL LASOTA | List possible risks that could happen in the project | DONE | 05/02/2023 - 05/02/2023
Judge the severities of all risks | 2023-02-05 | HIGH | PAWEL LASOTA | Judge the probabilities of all risks AND List possible risks that could happen in the project | DONE | 05/02/2023 - 05/02/2023
Describe different ways that these risks could be avoided or resolved | 2023-02-05 | HIGH | PAWEL LASOTA | List possible risks that could happen in the project | DONE | 05/02/2023 - 05/02/2023
Find examples of project management task allocations | 2023-02-06 | HIGH | PAWEL LASOTA |  | DONE | 06/02/2023 - 06/02/2023
Use excel to start plotting tasks as we go through the project | 2023-05-08 | HIGH | PAWEL LASOTA | Find examples of project management task allocations | IN PROGRESS | 01/02/2023 - 08/05/2023
Allocate each task to team member | 2023-05-08 | HIGH | PAWEL LASOTA | Use excel to start plotting tasks as we go through the project | IN PROGRESS | 01/02/2023 - 08/05/2023
Judge a deadline for each task | 2023-05-08 | HIGH | PAWEL LASOTA | Use excel to start plotting tasks as we go through the project | IN PROGRESS | 01/02/2023 - 08/05/2023
Ensure to include task dependencies for task prioritisation | 2023-05-08 | HIGH | PAWEL LASOTA | Use excel to start plotting tasks as we go through the project | IN PROGRESS | 01/02/2023 - 08/05/2023
Include up to date status on the task, e.g. if completed or not | 2023-05-08 | HIGH | PAWEL LASOTA | Use excel to start plotting tasks as we go through the project | IN PROGRESS | 01/02/2023 - 08/05/2023
Ensure to keep a log of conversations and critical conversation material | 2023-05-08 | HIGH | PAWEL LASOTA |  | IN PROGRESS | 01/02/2023 - 08/05/2023
Keep log of meetings and meeting descriptions and attendees | 2023-05-08 | HIGH | PAWEL LASOTA |  | IN PROGRESS | 01/02/2023 - 08/05/2023

## GANTT CHART
DILSTON SOFTWARE ENGINEERING PRACTICE GANTT CHART
[7 empty] | WEEK 1 | [6 empty] | WEEK 2 | [6 empty] | WEEK 3 | [6 empty] | WEEK 4 | [6 empty] | WEEK 5 | [6 empty] | WEEK 6 | [6 empty] | WEEK 7 | [6 empty] | WEEK 8 | [6 empty] | WEEK 9 | [6 empty] | WEEK 10 | [6 empty] | WEEK 11 | [6 empty] | WEEK 12 | [6 empty] | WEEK 13 | [6 empty] | WEEK 14
[8 empty] | 1-7 FEB | [6 empty] | 8-14 FEB | [6 empty] | 15-21 FEB | [6 empty] | 22-28 FEB | [6 empty] | 1-7 MAR | [6 empty] | 8-14 MAR | [6 empty] | 15-21 MAR | [6 empty] | 22-28 MAR | [6 empty] | 29 MAR - 4 APR | [6 empty] | 5-11 APR | [6 empty] | 12-18 APR | [6 empty] | 19-25 APR | [6 empty] | 26 APR - 2 MAY | [6 empty] | 3-9 MAY
[5 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9
[5 empty] | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T
Task | Lead | Timeline | Status | Days
Skills Audit & Proposal Milestone | ALL | 01/02/2023 - 17/02/2023 | DONE | 17
View the skills audit template | ALL | 01/02/2023 - 06/02/2023 | DONE | 6 | bar: 1 W to 1-7 FEB 6 M
Ensure all team members fill out their section of the skills audit | ALL | 06/02/2023 - 12/02/2023 | DONE | 6 | bar: 1-7 FEB 6 M to 8-14 FEB 12 S
Chat with team about the project idea & proposal | ALL | 12/02/2023 - 13/02/2023 | DONE | 1 | bar: 8-14 FEB 13 M to 8-14 FEB 14 T
Upon team agreement upon project idea, fill out the proposal section | ALL | 13/02/2023 - 14/02/2023 | DONE | 1 | bar: 8-14 FEB 14 T to 8-14 FEB 15 W
Ensure the skills audit is completed | ALL | 14/02/2023 - 15/02/2023 | DONE | 1 | bar: 8-14 FEB 15 W to 8-14 FEB 16 T
Hand in the skills audit | ALL | 15/02/2023 - 16/02/2023 | DONE | 1 | bar: 8-14 FEB 16 T to 8-14 FEB 17 F
Skills audit contingency (2 days) | ALL | 16/02/2023 - 17/02/2023 | DONE | 1
Organising Team Meetings/Communication Milestone | PAWEL LASOTA | 15/02/2023 - 16/02/2023 | DONE | 2
Find out availability from each member | PAWEL LASOTA | 15/02/2023 - 15/02/2023 | DONE | 1 | bar: 8-14 FEB 15 W to 8-14 FEB 16 T
Plan regular weekly meetings that match availability | PAWEL LASOTA | 16/02/2023 - 16/02/2023 | DONE | 1 | bar: 8-14 FEB 16 T to 8-14 FEB 17 F
Project Management Documentation Milestone | PAWEL LASOTA | 01/02/2023 - 08/05/2023 | IN PROGRESS | 96
View the Project Management Specification | PAWEL LASOTA | 01/02/2023 - 01/02/2023 | DONE | 1 | bar: 1 W
Gain a basic understanding of what is required | PAWEL LASOTA | 01/02/2023 - 01/02/2023 | DONE | 1 | bar: 1 W
Research examples of code of conduct documents | PAWEL LASOTA | 01/02/2023 - 01/02/2023 | DONE | 1 | bar: 1 W
Create a code of conduct document stating guidelines & rules within the team | PAWEL LASOTA | 02/02/2023 - 02/02/2023 | DONE | 1 | bar: 2 T
Ensure the document is signed by all team members | PAWEL LASOTA | 03/02/2023 - 03/02/2023 | DONE | 1 | bar: 3 F
Code of conduct contingency time (1 day) | PAWEL LASOTA | 04/02/2023 - 04/02/2023 | DONE | 1 | bar: 1-7 FEB 4 S
Research examples of risk analysis documents | PAWEL LASOTA | 05/02/2023 - 05/02/2023 | DONE
Create a document with a table with the risk, probability, severity and resolve | PAWEL LASOTA | 05/02/2023 - 05/02/2023 | DONE
List possible risks that could happen in the project | PAWEL LASOTA | 05/02/2023 - 05/02/2023 | DONE
Judge the probabilities of all risks | PAWEL LASOTA | 05/02/2023 - 05/02/2023 | DONE
Judge the severities of all risks | PAWEL LASOTA | 05/02/2023 - 05/02/2023 | DONE
Describe different ways that these risks could be avoided or resolved | PAWEL LASOTA | 05/02/2023 - 05/02/2023 | DONE
Find examples of project management task allocations | PAWEL LASOTA | 06/02/2023 - 06/02/2023 | DONE
Use excel to start plotting tasks as we go through the project | PAWEL LASOTA | 01/02/2023 - 08/05/2023 | IN PROGRESS | 96
Allocate each task to team member | PAWEL LASOTA | 01/02/2023 - 08/05/2023 | IN PROGRESS | 96
Judge a deadline for each task | PAWEL LASOTA | 01/02/2023 - 08/05/2023 | IN PROGRESS | 96
Ensure to include task dependencies for task prioritisation | PAWEL LASOTA | 01/02/2023 - 08/05/2023 | IN PROGRESS | 96
Include up to date status on the task, e.g. if completed or not | PAWEL LASOTA | 01/02/2023 - 08/05/2023 | IN PROGRESS | 96
Ensure to keep a log of conversations and critical conversation material | PAWEL LASOTA | 01/02/2023 - 08/05/2023 | IN PROGRESS | 96
Keep log of meetings and meeting descriptions and attendees | PAWEL LASOTA | 01/02/2023 - 08/05/2023 | IN PROGRESS | 96

## KEY
Status | STATUS | MEMBERS
DONE | HIGH | PAWEL LASOTA
IN PROGRESS | MEDIUM | JACK WELCH
TO BE DONE | LOW | CHARLIE JACK
STUCK |  | JOSH MARFLEET
ALL